Project Charter: [Menu Tablet Project]

DATE: [10/03/2025]

Project Summary

In order to cut down on customer wait times and boost sales, this initiative intends to install self-service tabletop menu tablets at every Sauce & Spoon location.

Project Goals

● Implement a tabletop menu tablet pilot program at two dining establishments. ● Concentrate By June, a bar area pilot will be launched. ● By June, raise the product mix (appetiser sales by 15% on average) ● Teach employees how to operate and handle new hardware and software ● Integrate system software for tablet and point-of-sale ● Reduce food waste by 25% by the end of the second quarter ● Hire two part-time kitchen personnel ● Cut table turn times by thirty minutes by June ● Increase the number of guests each day by ten percent by June ● Raise the average bill total by thirteen percent.

Deliverables

● Purchase and set up tablets for both sites ● Employ kitchen workers ● Expand appetisers ● Teach employees how to use the system ● Increase daily visitor count ● Shorten wait times at tables ● Cut down on food waste ● Integrate systems software

Scope and Exclusion

In-Scope: ● Establish a tabletop menu tablet pilot program at two restaurant locations ● Reduce food waste ● Increase part-time kitchen workers ● Shorten table turnover times ● Boost daily patronage ● Provide staff training Out-of-Scope: ● suggestion to include return policies in the launch ● suggestion to increase kitchen staff satisfaction ● reallocation of salary

Benefits & Costs

Benefits: - include accelerating service and other delivery procedures, turning tables faster, and serving more people. - Provide precise data points to monitor metrics so that we can contribute to the restaurant's prosperity. - stay abreast with the restaurant industry's expanding digital presence, which enables us to offer patrons a recognisable online experience. Costs: - Training supplies and charges --------------------> $ 10 000 - Implementation of Hardware and Software in Various Locations ----------> $ 30,000. - Upkeep (IT charges via EOY) --------------------> $ 5000 - New menu and website design charge --------------------> $ 5000 - Additional expenses for customisation --------------------> $ 500 - IN TOTAL The following: ------------------------------------------------------> $ 50,550

Appendix:

● aim misalignment with Deanna on shorter wait times for guests ● Proposal out of scope regarding the inclusion of return policies in the launch ● Proposal out of scope regarding enhancing kitchen staff satisfaction ● Lack of a clear aim for Installing tablet bundles with discounts and menu add-ons